## general_report
mine (AvePoint JIRA)
Displaying 27 issues at 30/Jan/15 8:42 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | A Improvement Type | % Complete (Review) | % Complete (Translation) | % Update | ADC Finished | APPS Progress | APPS Request ID | APPS Tracking Info | APPS Tracking Link | Account | Account Number | Actual Result | Affect Version for Test Request | Affected Hotfix Management | Affects Component/s in DocAve | Agent Hotfix Fixed | All products the customer is using | Apply License for Which Product | Apply License for Which version | Apply to NetApp | Approved/Not Approved | As a/an | Assigned To | Attachment Link | Automatically Created Issue | BURT Number | Batch Management | Behavior Expected | Behavior Observed | Branch Base on | Branch URL | Browser Type/s | Bug Causes Analysis | Build Environment URL | Build Environment URL Comment | Build Number | Business Value | CC FTP | CC Hotfix FTP Address | CCTeam Use_Attachment Category | CCTeam Use_Upload | CG Existing Customer | CI Causes Analysis | CI Coordinator | CI Fix Version in DocAve 6 | CI Leader | CI Solution Deliverable | CI Tester | CRM Change Type | CRM Customization Type | CRM Entity | Cannot sent hotfix reasons | Case Number | Censorious Account | Change Type | Changed Code/更改代码 | Checked Into Main Tree | China PM | China PM Reviewed | China Project | China Team Use_Resolution/解决方法 | Client Hotfix Management List Item URL | Client Submit | Code Reviewer | CodeChange | Comment/附注 | Common Related | Common Case | Competitor Functionality | Competitor Name | Competitor with Similar Functionality | Compliance Team Comments | Compliance Team Contact | Configuration/Architecture Change Details | Configuration/Architecture Change Impact | Configuration/Architecture Changes | Course Name | Create Art Design Task | Create Documentation Work | Create UX Design | Create VPAT | Current Solution “as is” | Customer | Customer Demo Feedback | Customer Importance | Customer Issue Status for DA6 | Customer Issue/客户问题 | Customer Region | Customer Type | Customer's Timeline | DL FTP | DL Hotfix FTP Address | Date Requested | Date Reviewed with Compliance Team | Date Sent to Product Team | Date of First Response | Dates Employed | Days spent in R&D | Deadline Promised Customer | Deal Size | Default Value of Build-in License | Delivered Hotfix # | Delivered Hotfix Counting | Delivery Date | Demo Number | Department | Dependency | Describe Proposed Feature | Developer/开发人员姓名 | Development Workload Estimation | Difficulty | Direction | Division | DocAve 6 Components Need Testing | DocAve 6 Database Name | DocAve 6 Function | DocAve 6 Hotfix Management List Item URL | DocAve 6 Hotfix Package | DocAve 6 Table Name | DocAve 6 Version for GA+ | DocAve Fix Required by GA+ | DocAve Related Functionality | Dynamics Case Link | Email Address | Encryption Software Name & Version/加密软件名称及版本 | End-Module Related | English Internationalization Team Work Status | English Summary | Enterprise | Epic Colour | Epic Link | Epic Name | Epic Status | Epic/Theme | Equivalent Hotfix/等同Hotfix | Error Information | Escalate Issue | Escalation Account | Escalation Action | Escalation Details | Evaluation | Event ID Bug | Existing Customer | Expected Result | Field for Obsoleted Issue Type | Fixed in Dev Branch | Flagged | French Internationalization JIRA Status | GA+ Hotfix Management List Item URL | GA+ Hotfix Package | GUI Bug Type | GUI Issue | GUI Review Database | GUI Update Work Status | Generate separate report or not | Generic Component Category | German Internationalization JIRA Status | German Internationalization Team Work Status | German Internationalization URL | Hotfix Fixed | Hotfix Info/Hotfix信息 | Hotfix Management List Item URL | Hotfix PM URL | Hotfix Package | Hotfix Solution | Hotfix Suggestion | Hotfix Used for | Hotfix Version | Hotfix merging status | HotfixUrl/Hotfix地址 | I want to | I18N Entries | IBM OEM Tech Support Verified | Included in DocAve6 Iteration Plan | Included in Iteration Plan | Integrated External System | Integration Tool | Internationalization Team Work Status | Internationalization Work Status | Invoice Number | Issue Existed in Previous Version/s | Issue Type for Backend Logic Enhancement | Issue Type for Internationalization | Issue from DocAve | Issue from SMSP Package | Issue in SP/CRM/DBP | JEP - Last Resolved User | JIRA Plugin Fix Version | Japan Internationalization JIRA Status | Japanese Internationalization Team Work Status | Japanese Internationalization URL | Language | Last Closed Date | Lecturer | Legal Requirement From Customer | License Charged by | Link to opportunity in CRM | Log Address in FTP | Log Information Status | MSF Task Role | MTC | Manager Hotfix Fixed | Merge into General Product | Merge into Product | Need End Module to Check | Need Maintenance | Need Product Confirmation | Need Tier2 Approval | Need to Change | NetApp Case Number | NetApp Company Name/Site ID | Notes | Number of Sending Hotfix | OS | Office | Official Name for the Newly Add Product/Module | On top of any POC Feature Pack | Optional Solution | Original Request | Other Customers | Other Way to Charge the License | PM Assignee | PMR Number | POC Tracking Info | POC Version | Package Installation | Package Needed | Packager/打包人员姓名 | Patch URL 2/Patch地址2 | Payment Override By | Payment State | Performace Test | Platform | Platform Support | Please input details | Potential Revenue | Probability of Deal Closed Win | Problem Description | Problem repeatable | Processing Dashboard | Product | Product Category | Product Component | Product Component Count | Product Internal Release Date | Product Module | Product Official Description | Product Version | Product Version Information | QA Assistance Comment | QA Workload Estimation | Quick Comment | Rank | Rank (Obsolete) | Readme for Manual Hotfix Installation\手动打hotfix方法说明 | Readme/自述文件 | Reason | Reason (Review) | Reason (Translation) | Reason for CG Issue | Reason for no review | Reason/打HOTFIX的原因 | Reassessment Reason | Related Bug ID/相关联的Bug ID | Release Notes Category | Reopening counter | Reopening histories of issue | Repeatability | Repeating Difficulty | Reproducible Issue | Request from CI | Require Configuration Change | Resolution from Compliance Team | Review Due Date | Review End Date | Review Interruption Interval(day) | Review Start Date | Root Cause | Round trips | SE/Sales | SMSP/DocAve 6 Issue | SQL Server | SVN Address | SVN Branch | Salesforce Case ID | Score | Scrum Master | Security Related Issue Description | Server Hotfix Management List Item URL | Server Submit | Severity | SharePoint | SharePoint Platform | SharePoint Version | SharePoint Version | So that | Solution Deliverable | Solution of Customer | Sprint | Stability | Stability Concerns | Steps to reproduce | Story Points | Sub fix version for Milestone | Support Status | Support Team | System Tester/测试人员姓名 | TSP Contact | Target/目标 | Task from US | Teacher Comment | Tech Support Verified | Test Case/测试步骤(用例) | Test Requester | Test Result for Configuration/Architecture Changes | Test Suggestion for QA | Test team to repeat the problem | The latest hotfix version from log | The relevant developer and QA | Tier 2 Support Status | Time in Preparing Build Environment Status | Timesheet Aggregation | Timesheet End Date | Timesheet Start Date | Title | Total Pages | Total Words | Training Date | Translation Completed | Translation Due Date | Translation End Date | Translation Interruption Interval(day) | Translation Start Date | Type/Hotfix类型 | US Developer | US Experts | US PM | US PM Ownership | US PM Reviewed | Unique Symptoms | Unsafe Change | Unsafe Change Review Status | Upload to APPS FTP | Use Cases | Verified by | Verified by Tester | Verify Log | Whether affect previous hotfix(es) | Whether exists Hotfix Management | Whether to include C-patch in hotfix | Wiki Link | Work-Arounds | Wrapper Change | Wrapper Component | [Obsoleted]Account Number | [Obsoleted]Assignee | [Obsoleted]Customer | [Obsoleted]Description | [Obsoleted]Encrypted by/加密人员姓名 | [Obsoleted]Need QA Test | [Obsoleted]Priority | [Obsoleted]Priority | [Obsoleted]Task Points | [Obsoleted]Verified By | [Upgrade Issue] Need to merge the previous hotfixes
MSF SG Enable | MSFSGE-2025 | AD Case状态为 Minimum Service Approved 之后触发 Timer | Improvement | Open | Major | Unresolved | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-29 09:19 | 2015-01-29 10:56 | 2015-01-29 10:21 |  | 1 |  | Adult Disability |  | 1 | [6 empty] | MSFSGE-2026 |  | CRM 中会有一个域 “Status Modify Date”，会记录Status Reason变化的时间，AD Case状态为 Minimum Service Approved 时，“Status Modify Date” 会记录状态更改的是间，Recommender 需要在 Alarm Setting 域中填写一个天数， 此时触发 Timer，到达这个天数时，通知 Recommender | [65 empty] | No | [38 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00t27: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [47 empty] | No
MSF SG Enable | MSFSGE-1739 | CRM blacklist：PWD由blacklist变为unblacklist后，在PWD上依然有blacklist的alert提醒 | Bug | Resolved | Major | Fixed | Ricky Wang | Qiuyang Mi | Qiuyang Mi | 2015-01-26 15:28 | 2015-01-29 16:03 | 2015-01-29 15:51 | 2015-01-29 15:51 | 1 | 1 | SGE Common |  | 2 | _thumb_682627.png _thumb_682628.png | [26 empty] | PWD提示为blacklist | [83 empty] | 2015-01-29 11:42 |  | 0 |  |  |  | 0 | [41 empty] | PWD上不应该再提示blacklist | [9 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦i00l5b: | 9.2234e+18 | [11 empty] | 0 |  | High | [10 empty] | 0 | [11 empty] | Not Provided | [10 empty] | 1.进入blacklist entity，选择一个PWD设置成blacklist（un-blacklist-no），审批通过 2.进入PWD记录，查看有alert提示是blacklist 3.再次进入blacklist entity，选择此PWD设置为unblacklist（un-blacklist-yes），审批通过后，查看此PWD状态 | [36 empty] | No
MSF SG Enable | MSFSGE-1724 | Black List 和Red List的PWD 需要在Case 上显示小黄条 | Backend Logic Enhancement | Resolved | Major | Fixed | Ricky Wang | Elina Chen | Elina Chen | 2015-01-26 11:38 | 2015-01-29 16:03 | 2015-01-29 15:58 | 2015-01-29 15:58 |  | 1 | SGE Common |  | 2 | [5 empty] | MSFSGE-1500, MSFSGE-1501, MSFSGE-1502, MSFSGE-1942, MSFSGE-1954 | [68 empty] | No | [36 empty] | 2015-01-29 15:58 |  | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [9 empty] | Task |  |  |  |  | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦i00kgf: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [47 empty] | No
MSF SG Enable | MSFSGE-1576 | MSFSGE-270 AD: auto calculate PWD and family member's age | Technical task | New Issue | Normal | Unresolved | Ricky Wang | Ethan Li | Ethan Li | 2015-01-22 13:52 | 2015-01-29 09:10 | 2015-01-22 13:52 |  |  | 1 | Adult Disability |  | 1 | [113 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00fjj: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [59 empty] | No
MSF SG Enable | MSFSGE-1549 | Expansion TP subgrid问题（databroker相关？） | UX Design | Open | Normal | Unresolved | Ricky Wang | Ethan Li | Ethan Li | 2015-01-22 10:27 | 2015-01-29 09:11 | 2015-01-22 10:27 |  |  |  | Adult Disability |  | 1 | [6 empty] | MSFSGE-1456, MSFSGE-1548 | [88 empty] | Yes | [17 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00erb: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [19 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1547 | 新提交的ad 申请逻辑判断+Duplicate ad case | UX Design | Open | Normal | Unresolved | Ricky Wang | Ethan Li | Ethan Li | 2015-01-22 10:26 | 2015-01-29 09:11 | 2015-01-22 10:26 |  |  |  | Adult Disability |  | 1 | [6 empty] | MSFSGE-1452, MSFSGE-1546 | [88 empty] | Yes | [17 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00eqn: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [19 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1500 | MSFSGE-1724 AD Case 如果这个PWD是在blacklist/redlist里，打开这个记录的时候，上面小黄条notification就会有个alert 提醒 | Technical task | New Issue | Major | Unresolved | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-21 17:51 | 2015-01-29 16:05 | 2015-01-29 16:05 |  | 1 | 1 | Adult Disability |  | 2 | [111 empty] | 2015-01-29 16:04 |  | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00dtr: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [59 empty] | No
MSF SG Enable | MSFSGE-1476 | MSFSGE-223 AD - Add naming convetion for uploading document | Technical task | New Issue | Major | Unresolved | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-21 14:09 | 2015-01-29 09:11 | 2015-01-21 14:09 |  | 1 | 1 | Adult Disability |  | 1 | [8 empty] | 详见主jira | [104 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00cov: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [59 empty] | No
MSF SG Enable | MSFSGE-1470 | 为AD 配置 Common Case Assignment 功能 | Improvement | Open | Major | Unresolved | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-21 13:16 | 2015-01-29 09:11 | 2015-01-22 10:11 |  | 1 | 1 | Adult Disability |  | 1 | _thumb_680565.png | [5 empty] | MSFSGE-45, MSFSGE-1529 |  | 创建case时，先根据 AD的特有的 Owner assign逻辑判断，涉及到 Common Case Assignment 的流程时，使用此功能 | [65 empty] | No | [38 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦hy3tkb: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [7 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1456 | Expansion TP subgrid问题（databroker相关？） | Story | Open | Normal | Unresolved | Ricky Wang | Ethan Li | Ethan Li | 2015-01-20 15:05 | 2015-01-29 09:11 | 2015-01-22 10:27 |  |  |  | Adult Disability |  | 1 | [6 empty] | MSFSGE-1548, MSFSGE-1549 | [67 empty] | No | [20 empty] | Yes | [17 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00306:r | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [19 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1455 | profiling部分多选域的配置 | Improvement | Ready for QA | Normal | Fixed | Ricky Wang | Ethan Li | Ethan Li | 2015-01-20 15:04 | 2015-01-29 10:34 | 2015-01-22 03:12 | 2015-01-21 13:57 |  | 1 | Adult Disability |  | 2 | [6 empty] | MSFSGE-1463 | [67 empty] | No | [36 empty] | 2015-01-21 13:57 |  | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦i00306:i | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [7 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1452 | 新提交的ad 申请逻辑判断+Duplicate ad case | Story | Open | Normal | Unresolved | Ricky Wang | Ethan Li | Ethan Li | 2015-01-20 14:42 | 2015-01-29 09:11 | 2015-01-22 10:26 |  |  |  | Adult Disability |  | 1 | [6 empty] | MSFSGE-1546, MSFSGE-1547 | [67 empty] | No | [20 empty] | Yes | [17 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00303: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [19 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1432 | AD CRM,Firefox浏览器登陆,option set类型value显示值缺少一行，且有空白value | Bug | Ready for QA | Major | Fixed | Ricky Wang | Qiuyang Mi | Qiuyang Mi | 2015-01-19 14:19 | 2015-01-29 10:35 | 2015-01-22 03:12 | 2015-01-21 14:29 | 1 | 1 | Adult Disability |  | 2 | _thumb_679215.png | [26 empty] | 第一个value显示为空；导致最后一个value显示不全 | [83 empty] | 2015-01-21 14:29 |  | 0 |  |  |  | 0 | [41 empty] | 显示正确，没有确实value | [9 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦i007o7: | 9.2234e+18 | [11 empty] | 0 |  | High | [10 empty] | 0 | [11 empty] | Not Provided | [10 empty] | Firefox登陆CRM环境：https://democrm.avepoint.net:50001/sgetest 进入AD case entity，查看assessment下option set显示的value值是否正确 | [36 empty] | No
MSF SG Enable | MSFSGE-1367 | 014_ADReferralCase_ReferralProcessingDetails2： Hide tabs (e.g. Pending - Trial Enrolment) based on the “Status Reason” of AD Referral Case | Improvement | Ready for QA | Normal | Fixed | Ricky Wang | Kiki Zhang | Kiki Zhang | 2015-01-15 17:56 | 2015-01-29 10:35 | 2015-01-21 09:20 | 2015-01-20 18:09 |  | 1 | Adult Disability |  | 2 | [6 empty] | MSFSGE-1459 | [67 empty] | No | [24 empty] | Yes | [11 empty] | 2015-01-20 17:21 |  | 0 |  |  |  | 0 |  |  | Demo2 | [48 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦i003jr: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [47 empty] | No
MSF SG Enable | MSFSGE-1343 | SGE Suggestion for Profiling | Improvement | Ready for QA | Normal | Fixed | Ricky Wang | Kiki Zhang | Kiki Zhang | 2015-01-15 16:58 | 2015-01-29 10:35 | 2015-01-22 03:12 | 2015-01-21 13:58 |  | 1 | Adult Disability |  | 3 | [6 empty] | MSFSGE-1344 |  | Profiling is needed for AD and non-AD services, it will be used to record assessment & recommendation done by the SGE officer after reviewing the case. Profiling is only for internal use; Add Textboxes for SGE officer to input their assessment; textboxes will be labelled accordingly to the different assessment being done. (format accordingly to the AD Access of fields) Fields please refer to attachment | [65 empty] | No | [24 empty] | Yes | [11 empty] | 2015-01-19 16:05 |  | 0 |  |  |  | 0 |  |  | Demo2 | [48 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦i0032n: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [47 empty] | No
MSF SG Enable | MSFSGE-1315 | 根据 Type of Application （多选域）显示/隐藏的 Service Details | Improvement | Closed | Major | Won't Fix | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-15 10:14 | 2015-01-29 10:35 | 2015-01-26 10:43 | 2015-01-26 10:43 | 1 | 1 | Adult Disability |  | 2 | _thumb_677543.png | [5 empty] | MSFSGE-1545 |  | 根据 Type of Application （多选域）的选择内容，显示/隐藏的 Service Details | [65 empty] | No | [36 empty] | 2015-01-26 10:43 |  | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [5 empty] | 2015-01-26 10:43 | [50 empty] | 1 | [8 empty] | 1¦i000rj: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [7 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1224 | AD - Mark Missing Documents | Improvement | Open | Normal | Unresolved | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-14 15:25 | 2015-01-29 09:11 | 2015-01-22 10:25 |  | 1 | 1 | Adult Disability |  | 1 | _thumb_677186.png | [5 empty] | MSFSGE-1544, MSFSGE-116 |  | AD FS 的2.3.1 Referral, Document and Eligibility Checking中 当 portal 端提到的Document 不全，在CRM端能够表现出来，提醒Officer | [65 empty] | No | [38 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦hzzy6f: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [7 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1211 | 多选域中勾选的内容不能被保存 | Bug | Closed | Critical | Fixed | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-14 13:13 | 2015-01-20 09:08 | 2015-01-21 13:27 | 2015-01-20 09:08 | 1 | 1 | SGE Common |  | 1 | _thumb_677022.png | [112 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [5 empty] | 2015-01-21 13:27 | [50 empty] | 1 | [8 empty] | 1¦hzzxk7: | 9.2234e+18 | [11 empty] | 0 |  | High | [10 empty] | 0 | [11 empty] | Not Provided | [10 empty] | 在多选域中勾选一些选项，进行保存，再次进入record 中进行查看，选择的信息没有被保存上 | [36 empty] | No
MSF SG Enable | MSFSGE-1077 | Case Status Rule 的定制 | Improvement | In Progress | Normal | Unresolved | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-08 19:56 | 2015-01-30 08:40 | 2015-01-28 13:50 |  | 1 |  | Adult Disability |  | 3 | [6 empty] | MSFSGE-1531 |  | 1.SGE Officer starts to choose AD services for PWD. SGE can choose one AD service as the main service case if the PWD has applied for more than one AD services or multiple AD services are suitable for this PWD. From now on, the application status changes will be based on the main service chosen 2.Each single service will then be referred to different service providers which splits every service into several referrals. All the status of the referrals are pre-set with ranking values. The service status will be auto-changed based on the pre-settled rule by the referral status. 详见FS | [65 empty] | No | [36 empty] | 2015-01-26 10:55 |  | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦hzwbf3: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [7 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-1076 | Disability Type 的映射 | Improvement | Closed | Major | Won't Fix | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-08 19:44 | 2015-01-29 10:36 | 2015-01-26 10:53 | 2015-01-26 10:53 | 1 | 1 | Adult Disability |  | 2 | [6 empty] | MSFSGE-1530 |  | 将AD Case上的Disability Type 映射到PWD Application | [65 empty] | No | [36 empty] | 2015-01-26 10:53 |  | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [5 empty] | 2015-01-26 10:53 | [50 empty] | 1 | [8 empty] | 1¦hzwbev: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [11 empty] | Not Provided | [7 empty] | SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-882 | MSFSGE-119 AD Case Number Rule | Technical task | Ready for QA | Major | Fixed | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-05 15:37 | 2015-01-15 13:11 | 2015-01-15 15:34 | 2015-01-15 13:11 | 1 | 1 | Adult Disability |  | 1 | [8 empty] | 包括 AD Case、AD Service Case、AD Referral Case 三个entity的 Case number | [104 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦hzzhpb: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [59 empty] | No
MSF SG Enable | MSFSGE-878 | MSFSGE-711 配置多选域 | Technical task | Ready for QA | Major | Fixed | Ricky Wang | Xiaopu Yang | Xiaopu Yang | 2015-01-05 14:53 | 2015-01-09 08:48 | 2015-01-09 03:05 | 2015-01-08 15:42 | 1 | 1 | Adult Disability |  | 1 | [8 empty] | 配置AD各个entity 中的多选域 详细字段见附件中，绿色高亮字段 | [104 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦hy3otz: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [19 empty] | SGE AD Sprint 1, SGE AD Sprint 2 | [39 empty] | No
MSF SG Enable | MSFSGE-242 | CRM反馈:PWD Entity--如果这个PWD是在blacklist/redlist里，打开这个记录的时候，上面小黄条notification就会有个alert 提醒 | Improvement | Closed | Trivial | Fixed | Ricky Wang | Kiki Zhang | Kiki Zhang | 2014-11-26 23:40 | 2015-01-29 10:36 | 2015-01-21 16:15 | 2014-12-24 13:11 |  | 1 | SGE Common |  | 4 | _thumb_672608.png | [5 empty] | MSFSGE-47 | [67 empty] | No | [24 empty] | Yes | [11 empty] | 2014-12-02 15:59 |  | 0 |  |  |  | 0 |  |  | Demo2 | [48 empty] | Not Start | [17 empty] | 0 | [14 empty] | Ricky Wang | [5 empty] | 2015-01-02 11:34 | [50 empty] | 1 | [8 empty] | 1¦hzy2ev: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [59 empty] | No
MSF SG Enable | MSFSGE-116 | Highlight Missing Documents | Backend Logic Enhancement | Resolved | Normal | Fixed | Ricky Wang | Zora Zhai | Zora Zhai | 2014-10-31 14:27 | 2015-01-27 11:06 | 2015-01-22 10:25 | 2014-12-18 11:17 |  | 1 | SGE Common |  | 2 | [5 empty] | MSFSGE-1475 | MSFSGE-1224, MSFSGE-1544 |  | Missing documents : when a case is created based on the submit from portal, crm could check some specific fields by workflow then create apostwith highlighted information of missing docs (or notify sge officers by email) Below are parts from functional specifications regarding Highlight Missing Documents Highlight Missing Documents there will be specific fields for each docs 1. The system will have a way to highlight the missing document to notify the SGE officer 2. Docs wrongly submitted, officer could indicate those docs in email (ribbon?) Reference in FS: 2.4.2.6 Document Completeness Checking Process & 2.5 Document management | [65 empty] | No | [36 empty] | 2014-11-27 12:42 |  | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [9 empty] | Task |  |  |  |  | Ricky Wang | [56 empty] | 1 | [8 empty] | 1¦hy3tkn: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [59 empty] | No
MSF RPG | MSFRPG-2163 | MSFRPG-1517 在CRM 中做一个solution，来配置timer所需参数 | Technical task | New Issue | Normal | Unresolved | Ricky Wang | Roy Yuan | Roy Yuan | 2015-01-12 16:11 | 2015-01-29 09:12 | 2015-01-12 16:11 |  |  |  | CMS Common |  | 1 | [8 empty] | 在CRM 中做一个solution，来配置timer所需参数,注意此solution，sge和rpg暂时可以用一个。 | [104 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦hzzty7: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [19 empty] | CRM Common Feature-Supert High | [39 empty] | No
MSF Common | MSFCMN-17 | 支持Genogram需要CRM定制 | Story | BA Review | Critical | Unresolved | Ricky Wang | Serena Zhang | Serena Zhang | 2015-01-26 18:02 | 2015-01-29 09:10 | 2015-01-26 18:26 |  |  |  | CRM Solution |  | 1 | [8 empty] | 附件为原始design 图，需要ADC改进，之后进行给客户demo后，需要客户提供详细data field。 designer：ada BA： robert QA： 待定 | [65 empty] | No | [38 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00mb3: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [59 empty] | No
MSF Common | MSFCMN-16 | 支持timeline 需求需要CRM定制 | Story | BA Review | Critical | Unresolved | Ricky Wang | Serena Zhang | Serena Zhang | 2015-01-26 17:59 | 2015-01-27 11:07 | 2015-01-26 17:59 |  |  |  | CRM Solution |  | 1 | [8 empty] | 根据tender，需要支持timeline功能，显示每个client名下所有的case BA： robert Designer： 于海龙 QA： pending | [65 empty] | No | [38 empty] | 0 |  |  |  | 0 | [51 empty] | Not Start | [17 empty] | 0 | [71 empty] | 1 | [8 empty] | 1¦i00ma7: | 9.2234e+18 | [11 empty] | 0 | [12 empty] | 0 | [59 empty] | No
Generated at Fri Jan 30 08:42:30 CST 2015 by Ricky Wang using JIRA 6.3.12#6343-sha1:0d8f4aafad7180503b3640e4b3fc2614bfaabae7.

## Sheet1
| 兄弟 | 父母监护人 | 子女 | 伴侣 | 其他家族成员 | 其他非家族成员
| 收养兄/弟（adopted） | 养父 | 养子 | 妻子
| 寄养兄/弟（forster） | 养母 | 养女 | 丈夫
| 收养姐/妹 | 父亲 | 女儿 | 伴侣
| 寄养姐/妹 | 母亲 | 儿子 | （姐妹夫）
| 兄弟 | 继父 | 继子 | （儿媳）
| 姐妹 | 继母 | 继女 | （女婿）
| 同父异母/同母异父有血缘兄/弟 | （岳父岳母） | （孙子） | （嫂子弟媳）
| 同父异母/同母异父有血缘姐/妹 | forster父 | （孙女） | （父母伴侣）
| 同父异母/同母异父无血缘姐/妹 | forster母
| 同父异母/同母异父无血缘兄/弟 | （祖父母）
（外祖父母）
（监护人）
1.forster和adopted是什么区别。
2.如果存在养父母和亲生父母同时存在的时候，tree该怎么表现，怎么布局。帮忙设计下。
3.确认一下，标红色的这几个关系我们将会去load。其他关系我们将不会显示。
4.标黄色的几种关系，现在无法确定到具体对象（比如存在多个儿子，多个儿媳的情况下,没法确定哪个儿媳是哪个儿子的媳妇儿） 我没会去查询儿子的related person关系，去找到wife信息匹配上去。